3. Scope Baseline

3.1 Scope objective

The CivicConnect baseline commits the team to a controlled, responsive web platform that provides a reliable and traceable way to submit, manage, monitor and report on service requests without creating an unsustainable technical, operational or financial burden. The boundary prioritizes the minimum business capabilities in the Master Project Brief and a smaller, complete, secure and testable solution over uncontrolled feature growth (Belgium Campus, 2026a).

3.2 In-scope capabilities

| Scope ID | Capability | Committed boundary |
| --- | --- | --- |
| S-IN-001 | Responsive web submission | A requester can submit a service request with validated essential information and a controlled category: facility fault, equipment damage, security concern, IT support, maintenance, lost property or other. |
| S-IN-002 | Requester status and history | An authenticated requester can view the current status and lifecycle history of an individual request and a list of their previously submitted requests. |
| S-IN-003 | Meaningful requester feedback | The platform provides in app feedback when a request is accepted, rejected, materially updated, resolved or closed. External email/SMS delivery is not committed. |
| S-IN-004 | Staff worklist | Authorized staff can view full details of relevant requests and search, filter and sort them using agreed useful criteria. |
| S-IN-005 | Triage and ownership | Authorized staff can correct categorization where permitted, assign a request or accept responsibility and view current ownership and ownership history. |
| S-IN-006 | Controlled request lifecycle | Authorized staff can update status through valid transitions and record actions, comments and resolution information. Actor and timestamp information is retained for auditability. |
| S-IN-007 | Resolution and closure | Authorized staff can resolve or close requests and provide resolution information. The detailed state model must address rejection, cancellation and reopening before requirements sign-off. |
| S-IN-008 | Role-based access | Requester, staff, supervisor/management and administrator capabilities are separated using role-based access and least privilege. |
| S-IN-009 | Oversight views | Authorized oversight users can identify open, overdue, resolved and closed requests and filter information by category and status. |
| S-IN-010 | Due-date/overdue basis | The system stores or derives a target resolution date using an approved rule so that overdue work can be identified. Automatic escalation is excluded. |

3.3 Out-of-scope items

| Scope ID | Excluded item | Boundary statement |
| --- | --- | --- |
| S-OUT-001 | Automated intake from WhatsApp, telephone or email | The baseline provides a single controlled web intake channel. Manual staff capture, if permitted by the client, must be specified separately and is not an automated integration. |
| S-OUT-002 | Native mobile applications | A responsive web interface is sufficient for this baseline. |
| S-OUT-003 | Multi-language localization | The baseline supports English only. |
| S-OUT-004 | Payment or billing | No financial transaction or invoicing workflow is included. |
| S-OUT-005 | AI-driven triage or routing | Categorization and assignment are controlled user actions where no predictive or generative routing is committed. |
| S-OUT-006 | Advanced analytics / BI | Only the oversight views in S-IN-009 are committed where forecasting, custom BI and data warehouses are excluded. |
| S-OUT-007 | External asset-management or HR integration | No external enterprise-system synchronization is included. |
| S-OUT-008 | Multi-organization / multi-tenant operation | The baseline serves one organization and one controlled deployment context. |

3.4 Deferred / future candidates

| Scope ID | Candidate | Conditions before consideration |
| --- | --- | --- |
| S-DEF-001 | SLA-based automatic escalation | Requires approved service targets, exception paths and notification rules. |
| S-DEF-002 | Email/SMS notifications | Requires provider, cost, consent, privacy, failure-handling and delivery decisions. |
| S-DEF-003 | Exportable analytics/reports | Requires approved formats, access rules, data minimization and reporting acceptance criteria. |
| S-DEF-004 | Attachment/photo upload | Requires storage limits, malware/content handling, access controls, retention and privacy analysis. |
| S-DEF-005 | Multi-channel automated intake | Requires external APIs, identity/correlation rules, security, availability and cost analysis. |

3.5 Deliberate exclusion defense: automated informal-channel intake

Excluded item: Automated intake from WhatsApp, telephone and email channels (S-OUT-001).

- Why it is attractive: These channels are named sources of fragmentation. Integrating them could reduce user behaviour change and appear to consolidate the current process directly.

- Schedule and resource rationale: A three-person academic team working across four milestones cannot responsibly commit to multiple third-party integrations while also specifying, constructing, securing, testing and deploying the core platform. The integration would materially increase dependency and schedule risk.

- Technology and security rationale: Messaging and email integrations introduce external authentication, rate limits, availability dependencies, identity matching, duplicate detection, consent and sensitive-data handling. Telephone intake additionally requires a defined transcription or staff-capture process.

- Value rationale: The core business value is a single controlled request record with visible ownership, status, history and oversight. A controlled web channel can deliver that value without external integrations. Multi-channel automation is therefore an enhancement, not a precondition for the baseline solution.

- Condition for reconsideration: After the core platform is stable, the client may request reconsideration. The team must analyse requirements, architecture, UI/API/data, privacy, quality/testing, scope, schedule/resources, cost, deployment, risk and technical debt before approval (Belgium Campus, 2026a).

3.6 Scope-to-Constraint Interactions

| Constraint area | Interaction with scope | Required control/evidence |
| --- | --- | --- |
| Schedule | External integrations, native apps and advanced analytics would compete with core workflow completion. | Keep excluded/deferred unless approved impact analysis shows capacity and no unacceptable milestone risk. |
| Cost/resources | Providers, hosting, storage and maintenance can create recurring costs beyond the academic team's capacity. | Record cost assumptions; prefer sustainable platform choices; approve new recurring costs explicitly. |
| Quality | Every scope item creates specification, usability, test, deployment and maintenance obligations. | Give committed capabilities measurable acceptance criteria and trace them through the RTM. |
| Security/privacy | Request data may be sensitive; broader access, uploads and integrations increase exposure. | Apply RBAC, least privilege, validation, secrets controls and security testing; record residual risks. |
| Operational burden | Complex configuration or multiple intake paths may undermine the stated need for sustainability. | Review administrative workflow and maintainability with STK-006 before approval. |

3.7 Scope Acceptance and Governance

This scope becomes the approved CivicConnect baseline after team review and PED v1.0 baseline sign-off. After approval, additions, removals or material changes must follow the project’s change-management process. Approved changes must be reflected in the scope baseline, requirements, Requirements Traceability Matrix and other affected controlled artefacts (Belgium Campus, 2026a).