| Risk ID | Description | Cause | Probability | Impact | Priority | Mitigation Strategy | Contingency Plan | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Failure to enforce role-based access, allowing requesters or staff to view unauthorized oversight information. | REQ-023 mandates strict jurisdiction visibility, which is complex to secure during early architectural phases. | Medium | High | Critical | Define strict authorization boundaries and route protection in Milestone 2 architecture planning. | Restrict system access entirely until authorization boundaries are verified. | Mohau Drew Modiselle (Backend) | Active |
| R02 | Password hashing fails or user credentials become exposed. | REQ-024 and REQ-030 require secure credential handling and encryption upon account creation | Low | High | Critical | Implement industry-standard encryption and security protocols before user registration is built. | Force a global password reset and patch the hashing vulnerability. | Mohau Drew Modiselle (Backend) | Active |
| R03 | System processing delays exceed the 10-second threshold. | Heavy filtering, sorting (REQ-015), and management statistics (REQ-013) calculations executed concurrently against the database. | Medium | Medium | High | Optimize database queries and indexing specifically for heavy filtering/sorting tasks. | Defer live statistical rendering in favor of asynchronous reporting. | Benno Weideman (Database/Lead) | Active |
| R04 | System crashes or degrades under load. | REQ-029 mandates support for 210 concurrent users, which strains unoptimized server resources | Medium | High | High | Design scalable server architecture and include load testing in the testing strategy. | Temporarily queue incoming user requests until capacity frees up. | Mohau Drew Modiselle (Backend) | Active |
| R05 | The backup database fails to execute a successful failover. | REQ-028 requires redundant database architecture, introducing complex synchronization dependencies. | Low | High | High | Define rigorous database redundancy and failover protocols in the Forward Engineering Considerations in M2 once tech stack is chosen | Initiate manual database restoration from the most recent safe snapshot. | Benno Weideman (Database/Lead) | Active |
| R06 | Submitted service request information becomes corrupted and the system fails to execute a rollback. | REQ-022 requires corruption-free storage and rollback mechanisms during transaction failures. Following CR-009, creating a single request now inherently spans multiple tables (service_request plus an initial action row). | Low | High | High | Enforce strict transactional database rules and atomic commits for all data ingestion. The Express API must wrap the service_request insert and the initial action insert inside a single BEGIN ... COMMIT block to guarantee a request is never saved without its creation date, assignee, and pending status. | Isolate the corrupted tables and restore the missing records from local logs. | Benno Weideman (Database/Lead) | Active |
| R07 | External API failures prevent the system from sending required status notifications via Gmail or SMS. | REQ-020 requires external platform integration, making the system reliant on third-party uptime. | Medium | Medium | Medium | Map out API rate limits and build robust error handling for external communication | Default to displaying in-app status updates (REQ-005) until API connectivity is restored. | Tammy Fourie (Frontend/Design) | Active |
| R08 | Platform interface fails to function or render correctly across phone, tablet, laptop, and desktop devices. | REQ-025 requires compatibility across phone, tablet, laptop, and desktop interfaces. | High | Medium | High | Commit to a highly responsive UI framework in the Milestone 2 technology selection. | Enforce a desktop-first deployment until mobile layouts are stabilized. | Tammy Fourie (Frontend/Design) | Active |
| R09 | Scope creep driven by the high volume of complex "High" priority features (e.g., auditing staff actions, REQ-016) leads to premature M1 coding. | High volume of complex "High" priority features (e.g., REQ-016 auditing) tempting developers to build before baselining. | High | Medium | High | Strictly bind these complex requirements to future milestones and lock the PED v1.0 scope baseline. | Revert any premature implementation branches and refocus on documentation. | Tammy Fourie (or Benno Weideman) | Active |
| R10 | Layer and module boundaries erode; controllers start to contain SQL or business rules. | Deadline pressure; layering is new to the team (D09). | Medium | Medium | Medium | Dependency rules in the PR checklist now; ESLint import rule in M3. | Refactor the offending module before the M3 merge freeze. | Mohau Drew Modiselle (Backend) | Active |
| R11 | Status names differ between screens, API, database and tests. | CR-003 not approved or not applied everywhere (REQ-003, REQ-010, REQ-012, REQ-014, §8.1, §12.2) | Medium | High | High | One status enum in the domain layer (D10); UI reads labels from the API; CHECK constraint in PostgreSQL. | Map old labels at the API until CR-003 is closed. | Mohau Drew Modiselle or Benno Weideman | Active |
| R12 | Wireframes do not match what requesters understand (category names, error wording, confirmation email). | No one outside the team has tried the design yet. | Medium | Medium | Medium | One walkthrough with a non-team participant before the forms are built (§10.6). | Change labels and wording; cheap before build. | Tammy Fourie | Active |
| R13 | Accessibility defects are found late, when styling is applied. | Wireframes are greyscale; contrast and keyboard use untested. | Medium | Medium | Medium | Automated contrast and keyboard checks in the M3 quality gates (§10.4). | Fix before release; record residual issues. | Tammy Fourie | Active |
| R14 | Confirmation emails are delayed, blocked or land in spam, so new users cannot activate their account. | Email verification at registration (D13) depends on email delivery. | Medium | High | High | Provider with SPF/DKIM set up; "resend confirmation email" on the check-email page and sign-in error; delivery tested in M3. | Administrator can mark an account as verified after checking identity; switch provider through the MailSender adapter (D11). | Mohau Drew Modiselle | Active |
| R15 | Unconfirmed accounts build up (typos, abandoned or automated sign-ups). | Accounts stay unconfirmed when the link is never opened (D13). | Medium | Low | Low | Rate limits on registration; unconfirmed accounts deleted after 7 days by a scheduled clean-up. | Manual clean-up query by the administrator. | Mohau Drew Modiselle & Tammy Fourie | Active |
| R16 | Free-tier email quota is exceeded, so confirmation and notification emails stop. | ASR-001 (R0 budget) limits provider choice; every registration and (if CR-005) status change sends an email. | Low | Medium | Medium | Rate limits per email and IP; check provider quotas when choosing in M3 (CON-CST-03). | Pause status emails first (in-app feedback continues), keep confirmation emails. | Benno Weideman & Mohau Drew Modiselle | Active |